## Status Report Template
Status Report for Team 1
Project |  | Status: (Red/Yellow/Green)
Date: |  | Overall Status: | Green
Contact: |  | Explanation:
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
Green
Green
Green
Green
Green
Green
Green
Green
Green
Green

## 261005-StatusReport
Status Report for Team 1
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2026-10-05 |  | Overall Status: | Green
Contact: | via mthree email/teams |  | Explanation: | We've mostly planned our user stories, class diagram and ERD last week. User stories have also been grouped into work packages and organised on a scrum board on GitHub. And, we're ready to start development today.
Prepared By: | Vrishti
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task |  | Date Completed | Comment
Team effort | Planned User Stories |  | 2026-10-01
Team effort | Planned ERD |  | 2026-10-02
Team effort | Planned Class Diagram |  | 2026-10-02
Vrishti | Setup a Scrum Board on GitHub |  | 2026-10-05
Vrishti | Initial Project Setup on GitHub |  | 2026-10-05 | Allowing team to split-up and start working on tasks today
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
[As listed in issues/tasks on GitHub] |  |  |  |  | Testing as we go through features
Security & User Setup |  |  | Green | 2026-10-06 | Vrishti - Okay. Best to set-up for security now to avoid potential issues later | 0%
API Setup & Food Lookup |  |  | Green | 2026-10-06 | Saif - Okay | 0%
Client Goals |  |  | Green | 2026-10-06 | Favour - Okay | 0%
Consultant Clients |  |  | Green | 2026-10-06 |  | 0%
Food Diary Entries |  |  | Green | 2026-10-07 |  | 0%
Tracking Goals |  |  | Green | 2026-10-07 |  | 0%
Daily Diary Feedback |  | Stretch | Green | 2026-10-07 |  | 0%
Food Recommendations |  | Stretch | Green | 2026-10-08 |  | 0%
User Management Plus |  | Stretch | Green | 2026-10-08 |  | 0%
Presentation Preparation |  |  | Green | 2026-10-09 |  | 0%
Client Recipies |  | v2.0 |  |  |  | 0%
Recipe Recommendations |  | v2.0 |  |  |  | 0%