## Status Report Template
Status Report for Team 1
Project |  | Status: (Red/Yellow/Green)
Date: |  | Overall Status: | Green
Contact: |  | Explanation:
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
Green
Green
Green
Green
Green
Green
Green
Green
Green
Green

## 261005-StatusReport
Status Report for Team 1
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2026-10-08 |  | Overall Status: | Green
Contact: | via mthree email/teams |  | Explanation: | Backend is mostly finished. A few features are being implemented in the frontend.
Prepared By: | Saif
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task |  | Date Completed | Comment
Team Effort | Planned User Stories |  | 2026-10-01
Team Effort | Planned ERD |  | 2026-10-02
Team Effort | Planned Class Diagram |  | 2026-10-02
Vrishti | Setup a Scrum Board on GitHub |  | 2026-10-05
Vrishti | Initial Project Setup on GitHub |  | 2026-10-05 | Allowing team to split-up and start working on tasks today
Team Effort | Prepared for the presentation |  | 2026-10-08 | Prepared a presentation and carried out a dry run
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  | Priority | Health | Due Date | Comment | Status %
[As listed in issues/tasks on GitHub] |  |  |  |  | (Testing as we go through features - hopefully)
Security & User Setup |  |  | Green | 06/10/2026 1pm | Vrishti - Done. Best to set-up for security now to avoid potential issues later | 100%
API Setup & Food Lookup |  |  | Green | 06/10/2026 1pm | Saif - Done. | 100%
Client Goals |  |  | Green | 06/10/2026 1pm | Favour - Done. | 100%
Consultant Clients |  |  | Green | 06/10/2026 1pm | Vrishti - Done. | 100%
Food Diary Entries |  |  | Green | 07/10/2026 1pm | Saif - Done. | 100%
Barcode Scanner |  |  | Green | 08/10/2026 1pm | Vrishti - Done | 100%
Presentation Dry-Run |  |  | Green | 08/10/2026 3pm | Completed the dry run | 100%
Tracking Goals |  | Stretch | Green | 08/10/2026 6pm | Favour | 50%
Frontend for food diary |  |  | Green | 08/10/2026 6pm |  | 50%
Presentation |  |  | Green | 09/10/2026 1pm | In the process of polishing up the powerpoint | 50%
Daily Diary Feedback |  | Stretch | Green | 07/10/2026 1pm | leave out stretch goals to priotise quality over quantity with the time we have left | 0%
Food Recommendations |  | Stretch | Green | 08/10/2026 1pm |  | 0%
User Management Plus |  | Stretch | Green | 08/10/2026 1pm |  | 0%
Client Recipies |  | v2.0 |  |  |  | 0%
Recipe Recommendations |  | v2.0 |  |  |  | 0%

## 261006-StatusReport
Status Report for Team 1
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2026-10-06 |  | Overall Status: | Green
Contact: | via mthree email/teams |  | Explanation:
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task |  | Date Completed | Comment
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  | Priority | Health | Due Date | Comment | Status %
[As listed in issues/tasks on GitHub] |  |  |  |  | (Testing as we go through features - hopefully)
Security & User Setup |  |  | Green | 06/10/2026 1pm |  | 10%
API Setup & Food Lookup |  |  | Green | 06/10/2026 1pm |  | 0%
Client Goals |  |  | Green | 06/10/2026 1pm |  | 10%
Consultant Clients |  |  | Green | 06/10/2026 1pm |  | 10%
Food Diary Entries |  |  | Green | 07/10/2026 1pm |  | 0%
Tracking Goals |  |  | Green | 07/10/2026 1pm |  | 0%
Daily Diary Feedback |  | Stretch | Green | 07/10/2026 1pm |  | 0%
Food Recommendations |  | Stretch | Green | 08/10/2026 1pm |  | 0%
User Management Plus |  | Stretch | Green | 08/10/2026 1pm |  | 0%
Presentation Dry-Run |  |  | Green | 08/10/2026 3pm |  | 0%
Presentation |  |  | Green | 09/10/2026 1pm |  | 0%
Client Recipies |  | v2.0 |  |  |  | 0%
Recipe Recommendations |  | v2.0 |  |  |  | 0%
Discuss deadlines